## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## NOTES
|  | Responsible | DDL
Feature 1 | 1- Dashboard interface HTML ( Layout ) | M | The 5th evening
· In the program, functionality needed is for admin to add, edit and remove candidates. | 2- DB of LOGIN | V | the 4th evening
| 3- Java servlt for Add | N & W | the 6th
4- Java servlt for edit
5- Java servlt for remove
Feature 2 | 1- Answers interface HTML ( Layout ) | W | The 5th evening
· In the program, functionality needed is for candidates to answer the questions and edit and delete their answers. | 2- DB of Answers | N | The 5th evening
| 3- Java servlt for Add qst | V & M | the 6th
4- Java servlt for edit qst
5- Java servlt for remove qst
Feature 3 | 1- User interface HTML ( Layout ) | N | the 9th
· In the program, functionality needed for an end user to answer the questions | 2- DB of Answers | W | the 9th
Note on B2: ====== ID#AAAAXY59Azo Wafa Faquir (2022-04-04 13:18:03) add edit and remove

## ProductBacklog
Product Backlog - Election machine |  |  | Priorities
User Story | Story Point(s) | Priority (1-5) | high | medium | low
As a user, I am able to answer the questions. | 2 | 1 | 1 | 3 | 5
As a user, I am able to see the best candidate for me. | 4 | 1
As a user, I am able to compare my answers to the candidates' answers. | 4 | 1
As a user, I am able to see the information of the second candidate and the third etc. | 4 | 4
As a user, I am able to see all the cadidates. | 1 | 3
As a user, I am able to filter candidates by their party. | 1 | 4
As an admin, I am able to log in. | 2 | 1
Finishing the project | 2 | 1
As an admin, I am able to add, read, edit and remove candidates. | 3 | 2
As an admin, I am able to add, read, edit and remove election machine questions. | 3 | 2
As a candidate I can modify my answers | 2 | 5
As a candidate I can answer the questions | 2 | 5

## All tasks
Responsible | SUMMARY
All | User stories and their tasks | Done
Not associated with a user story
Coding the layout
- | As a user, I am able to answer the questions. | X
Coding the UI
Read questions from the database
Save the answers as objects in the session
- | As a user, I am able to see the best candidate for me. | X
Coding the UI
Compare the user's and candidates' answers
Read candidates and their answers from the database
Coding the comparison algorithm
- | As a user, I am able to compare my answers to the candidates' answers. | X
Coding the UI
Read candidates and their answers from the database
Compare the user's and candidates' answers
Show the user's answers next to the candidates' answers
- | As a user, I am able to see the information of the second candidate and the third etc. | X
Coding the UI
Search the other candidates from the database
ALL | As a user, I am able to see all the cadidates. | Done
Coding the UI
Read candidates from the database
- | As a user, I am able to filter candidates by their party. | X
Coding the UI
Read candidates and their parties from the database
Create dropdown list
ALL | As an admin, I am able to add, read, edit and remove candidates. | Done
Coding the UI
Methods for adding, reading, editing and removing the candidates
- | As an admin, I am able to add, read, edit and remove election machine questions. | X
Coding the UI
Methods for adding, reading, editing and removing the questions
ALL | As an admin, I am able to log in. | Done
Coding the UI
Create admin username and password
Encrypt password
Add log in page
Compare the login credentials provided by the user to the credentials saved to the database + notifications for the user
Create link to the admin page
Create a database connection and get the admin username and password from there
ALL | Finishing the project
| Add autoincrement to MySQL | x
| Check that the navigation bars are the same in every page | done
| Check that the design is the same in every page | done
| Check that every feature works | done
| Solve the UTF-8 problems | done
| Comment the code | done
| Check the link, variable and function names | done
| Combine all the codes | done
| Create javadoc | done
- | As a candidate I can modify my answers | X
Coding UI
Update candidates answers to database
- | As a candidate I can answer the questions | X
Coding UI
Add candidates answers to database

## sprint_planning_meetings
Spring Planning | Participants
Week 1 | Vignesh Kandi | Nazanin Fallah | Mona Achaaoud | Wafa Faquir
Physically | X | X | X | X | If physically present mark X
2022-03-29
What needs to be done: The following features are done: The user can answer to the questions, see the information of all of the candidates and filter the candidates by their party. Also the admin can log in to the system and read,edit, remove and add election machine candidates.
How will it be done: Each member of the team will pick a User Story and implement it.
Week 2 | Vignesh Kandi | Nazanin Fallah | Mona Achaaoud | Wafa Faquir
Physically | X | X | X | X
2022-04-04
What needs to be done: The following features are done: The user can answer questions. The admin can add, read, edit and remove the election machine questions. The user can see the best and the second best etc candidates for them. The user can also compare their answers to the candidates' answers.
How will it be done: The tasks are divided between the members of the group and implemented. Answering to questions should be done first.
Week 3 | Vignesh Kandi | Nazanin Fallah | Mona Achaaoud | Wafa Faquir
Online | X | X | X | X
2022-04-07
What needs to be done: The goal of the sprint is to check that everything in the project works fine and the design looks same everywhere and the code is commented well. In addition, MySQL has autoincrement in the id fields.
How will it be done: We will check both individually and together that everything works
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## Sprint Reviews
Sprint 1 | X = done |  | Sprint 3 | X = done
What we were supposed to do | What we were able to do | What we were not able to do | What we were supposed to do | What we were able to do | What we were not able to do
Code the layout | X |  | Add autoincrement to MySQL |  | x
Set up Github | X |  | Check that the navigation bars are the same in every page | X
Study the needed technologies | X |  | Check that the design is the same in every page | X
The user is able to answer the questions | We were able to get the questions from the database and the UI shows them for the user. | The user can't yet answer to the questions. | Check that every feature works | X
The user is able to see all the candidates | X |  | Solve the UTF-8 problems | X
The user is able to filter the candidates by their party | X |  | Comment the code | X
The admin is able to log in | X |  | Check the links | X
The admin, is able to add, read, edit and remove candidates. | Add, read, and remove candidates are done. | Edit is done, but it doesn't work. | Combine all the codes | X
|  |  | Create javadoc | X
|  |  | Candidate can modify his/hers answers | X
Sprint 2 | X = done |  | Candidate can answer the questions | X
What we were supposed to do | What we were able to do | What we were not able to do
As an admin, I am able to add, read, edit and remove election machine questions. | X
As a user, I am able to answer the questions (Continue the task from the last sprint) | X
As a user, I am able to see the best candidate for me. | X
As a user, I am able to see the information of the second candidate and the third etc.
As an admin, I am able to edit candidates in database (Continue the task from the last sprint) | X
As a user, I am able to compare my answers to the candidates' answers. | X

## sprint_backlog_sprint1
Sprint Backlog : Sprint 1 ( darker grey = Not going to do it )
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | Goal of the sprint
|  |  |  | Hours used to do the task | Hours used to do the task | Hours used to do the task | Hours used to do the task | Hours used to do the task | All the tasks of the user stories are done: The user can answer to the questions, see the information of all of the candidates and filter the candidates by their party. Also the admin can log in to the system and read,edit,remove and add election machine candidates.
Set up Github |  | All | Done | 2
Studying with videos |  | All | Done | 2 | 2
As a user, I am able to answer the questions |  | All
Coding the UI |  |  | Ongoing
Read questions from the database |  |  | Ongoing
Save the answers for comparing |  |  | Ongoing
As an admin, I am able to add, read, edit and remove candidates. |  | All
Coding the UI |  |  | Done | 3
Method for adding candidates to database |  |  | Done |  | 4
Method for reading the candidates from the database |  |  | Done |  |  | 3 | 2 | 5
Method for editing the cadidates in database |  |  | Done |  |  | 2 | 1 | 4
Method for removing candidates from database |  |  | Done |  |  |  |  | 5
Not associated with a user story |  | All
Coding the layout-Home page |  |  | Done |  | 4
As a user, I am able to see all the cadidates. |  | All
Coding the UI |  |  | Done |  |  |  | 3
Read candidates from the database |  |  | Done |  |  |  |  | 2
As an admin, I am able to log in |  | All
Coding the UI |  |  | Done |  |  | 1
Create admin username and password |  |  | Done |  |  | 1
Encrypt password |  |  | - |  |  |  |  | 1
Add log in page |  |  | Done |  |  | 2
Create a database connection and get the admin username and password from there |  |  | Done
Compare the login credentials provided by the user to the credentials saved to the database + notifications for the user |  |  | Done
Create link to the admin page |  |  | Done |  |  |  | 1
As a user, I am able to filter candidates by their party. |  | All
Coding the UI
Create dropdown list
Read candidates and their parties from the database
TOTAL |  |  |  | 7.5 | 4 | 6 | 7.32 | 17.82

## sprint_backlog_sprint2
Sprint Backlog : Sprint 2 ( RED = We code it but a problem was accuring )
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | Goal of the sprint
As an admin, I am able to add, read, edit and remove election machine questions. | 3 | All | [6 empty] | All the tasks of the user stories are done: The admin can add, read, edit and remove the election machine questions and in addition the admin can edit candidates in the database. The user can see the best and the second best etc candidates for them. The user can also compare their answers to the candidates' answers.
Coding the UI |  |  | Ongoing | 4
Method for adding questions to database |  |  | Ongoing |  | 2
Method for reading the questions from the database |  |  | Ongoing |  |  | 1
Method for editing the questions in database |  |  | Ongoing |  |  | 2 | 1
Method for removing questions from database |  |  | Ongoing |  |  |  |  | 3
As a user, I am able to answer the questions (Continue the task from the last sprint) | 2 | All
Save the answers for comparing |  |  | Ongoing
As a user, I am able to see the best candidate for me. | 4 | All
Coding the UI |  |  | x
Compare the user's and candidates' answers |  |  | x
Read candidates and their answers from the database |  |  | x
Coding the comparison algorithm |  |  | x
Adding more test data |  |  | x
As a user, I am able to see the information of the second candidate and the third etc. | 4 | All
Coding the UI |  |  | x
Search the other candidates from the database |  |  | x
As an admin, I am able to edit candidates in database (Continue the task from the last sprint) | 4 | All
Method for editing the cadidates in database | [7 empty] | 6
As a user, I am able to answer the questions |  | All
Coding the UI |  |  | Ongoing |  |  | 3
Read questions from the database |  |  | Ongoing |  |  |  |  | 3
Save the answers for comparing |  |  | Ongoing
TOTAL |  |  |  | 0.16 | 2 | 8.24 | 1.16 | 12.66

## sprint_backlog_sprint3
Sprint Backlog : Sprint 3
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | Goal of the sprint
Finishing the project | 2 | All | [6 empty] | The goal of the sprint is to check that everything in the project works fine and the design looks same everywhere and the code is commented well. In addition, MySQL has autoincrement in the id fields.
Add autoincrement to MySQL |  |  | x achieve |  |  |  |  | 3
Check that the navigation bars are the same in every page |  |  | done |  | 1 | 1
Check that the design is the same in every page |  |  | done |  |  |  |  | 3
Check that every feature works |  |  | done |  |  |  |  | 1
Solve the UTF-8 problems |  |  | x achieve
Comment the code |  |  | done |  |  |  |  | 4
Check the links |  |  | done |  |  |  |  | 1
Combine all the codes |  |  | done |  |  |  |  | 1
Create javadoc |  |  | done |  |  |  |  | 1
As a candidate I can modify my answers | 2 | All
Coding UI |  |  | x achieve | 3 | 2 | 4 | 5
Update candidates answers to database |  |  | x achieve
As a candidate I can answer the questions | 2 | All
Coding UI |  |  | x achieve | 3 | 4 | 1 | 2
Add candidates answers to database |  |  | x achieve
As an admin, I am able to add, read, edit and remove election machine questions. | 3 | All
Coding the UI |  |  | x achieve | 2
Method for adding questions to database |  |  | x achieve | 1 | 2
Method for reading the questions from the database |  |  | x achieve |  | 1 | 1
Method for editing the questions in database |  |  | x achieve |  |  |  | 3
Method for removing questions from database |  |  | x achieve
As a user, I am able to answer the questions |  | All
Coding the UI |  |  | x achieve |  |  | 3
Read questions from the database |  |  | x achieve |  |  |  |  | 3
Save the answers for comparing |  |  | x achieve
TOTAL |  |  |  | 6 | 7 | 6 | 7 | 14